WEEK 1 INTERNSHIP TASK

Project Planning & Requirements Analysis

Hypothetical Project: CampusConnect — Student Academic & Service Management System

Prepared for: Junior Software Developer Internship
Document Type: Project Planning & Requirements Analysis
Version: 1.0 | Date: 5 October 2026

# 1. Executive Summary

This document presents a detailed project planning and requirements analysis for CampusConnect, a hypothetical web-based Student Academic & Service Management System. The purpose of the system is to bring common student services—academic announcements, class schedules, assignment tracking, attendance visibility, service requests, and notifications—into one secure platform. The project is designed as an internship-level software development exercise and demonstrates how a software team can move from an initial business problem to clear requirements, a controlled scope, an achievable timeline, measurable milestones, and risk-management actions.

The planning approach combines stakeholder interviews, questionnaires, observation, document review, user stories, use cases, acceptance criteria, and requirements prioritization. The project will use a phased software development lifecycle with requirements, design, development, testing, deployment, and review activities. The expected result is a maintainable minimum viable product (MVP) that can later be expanded with advanced analytics, mobile applications, integrations, and automation.

# 2. Project Overview

## 2.1 Project Idea

CampusConnect is a responsive web application for students, faculty, and administrators. Students can view their timetable, receive announcements, track assignments, monitor attendance information, and submit service requests. Faculty can publish announcements, manage assignment information, and respond to student requests. Administrators manage users, roles, academic data, and system-level reports.

## 2.2 Problem Statement

In many educational environments, important information is distributed across notice boards, email, messaging groups, spreadsheets, and separate portals. This fragmentation can cause missed deadlines, duplicate work, slow service responses, and difficulty locating current information. CampusConnect addresses this problem by providing a single role-based platform and a consistent source of information.

## 2.3 Target Audience

| Stakeholder | Needs | Expected Value |
| --- | --- | --- |
| Students | Schedules, announcements, assignments, requests | Convenience and timely information |
| Faculty | Publish academic information and manage requests | Less repetitive communication |
| Administrators | User management, reports, oversight | Centralized control and visibility |
| Management | High-level service and usage information | Better operational decisions |

## 2.4 Business Use Cases

A student checks the current timetable before attending class.

A faculty member publishes an assignment with a deadline and instructions.

The system sends an in-app notification when an important announcement is published.

A student submits a service request and tracks its status from submitted to resolved.

An administrator creates or disables accounts and assigns appropriate roles.

Management reviews basic reports such as active users, request volumes, and resolution status.

# 3. Project Objectives

Create a single, easy-to-use platform for core student academic and service information.

Reduce dependency on scattered communication channels for routine academic updates.

Provide role-based access so students, faculty, and administrators see appropriate functions.

Improve visibility of assignments, announcements, schedules, and service requests.

Maintain an auditable status history for service requests.

Deliver a secure, responsive MVP suitable for desktop and mobile browsers.

Establish clear requirements and acceptance criteria before major development begins.

Measure success through usability, reliability, requirement coverage, and stakeholder acceptance.

# 4. Stakeholder & Requirements Elicitation Plan

Requirements elicitation is the process of discovering what users and stakeholders actually need, rather than assuming that the development team already knows the answer. For CampusConnect, the requirements process will start with stakeholder identification, followed by structured interviews, questionnaires, observation, document analysis, and validation workshops.

| Technique | How it will be used | Output |
| --- | --- | --- |
| Interviews | Speak with students, faculty, and administrators using a question guide. | Needs, pain points, priorities |
| Questionnaire | Collect feedback from a wider student group. | Frequency and preference data |
| Observation | Observe how announcements and service requests are currently handled. | Current-process map |
| Document analysis | Review existing forms, notices, policies, and spreadsheets. | Business rules and constraints |
| Workshop | Review proposed requirements with stakeholders. | Validated requirements |
| Prototype review | Show simple screens/wireframes before development. | Usability feedback and corrections |

A practical reference for requirements work is the ISO/IEC/IEEE 29148 requirements-engineering approach, which emphasizes clear, verifiable, necessary, feasible, and traceable requirements. User stories and acceptance criteria will also be used to keep requirements understandable to both technical and non-technical stakeholders.

# 5. User Requirements

## 5.1 User Personas

| Persona | Description | Primary Goals |
| --- | --- | --- |
| Student | Uses the system mainly to consume information and submit requests. | Find information quickly; track academic work |
| Faculty Member | Publishes and manages academic information. | Communicate updates efficiently |
| Administrator | Controls accounts, roles, and operational data. | Maintain accurate and secure system data |

## 5.2 User Stories

| ID | Role | User Story |
| --- | --- | --- |
| US-01 | Student | I want to log in securely so that I can access my personalized dashboard. |
| US-02 | Student | I want to view my timetable so that I know when and where classes occur. |
| US-03 | Student | I want to view assignments and due dates so that I can plan my academic work. |
| US-04 | Student | I want to submit a service request so that I can ask the institution for help. |
| US-05 | Student | I want to track my request status so that I know whether it is being handled. |
| US-06 | Faculty | I want to publish announcements so that students receive official updates. |
| US-07 | Faculty | I want to add assignment details so that students have clear instructions and deadlines. |
| US-08 | Administrator | I want to manage users and roles so that access remains appropriate. |
| US-09 | Administrator | I want to view service-request reports so that operational issues can be monitored. |
| US-10 | All Users | I want the interface to work on mobile and desktop browsers so that I can use it conveniently. |

## 5.3 Use Cases

| Use Case | Actor | Main Flow | Expected Result |
| --- | --- | --- | --- |
| UC-01 Login | All users | Enter credentials → validate → open dashboard | Authenticated session |
| UC-02 View timetable | Student | Open timetable → select date/week | Current schedule displayed |
| UC-03 Publish announcement | Faculty | Create announcement → preview → publish | Announcement visible to intended users |
| UC-04 Submit request | Student | Choose category → describe issue → submit | Request ID and status created |
| UC-05 Resolve request | Faculty/Admin | Open request → update status → add response | Status and history updated |
| UC-06 Manage users | Admin | Search user → edit role/status → save | User account updated with audit record |

# 6. Functional Requirements

| ID | Area | Requirement |
| --- | --- | --- |
| FR-01 | Authentication | The system shall allow registered users to sign in using approved credentials. |
| FR-02 | Role-based access | The system shall restrict features according to Student, Faculty, and Administrator roles. |
| FR-03 | Dashboard | The system shall display relevant announcements, upcoming assignments, and request status. |
| FR-04 | Timetable | The system shall allow students to view their assigned classes by day/week. |
| FR-05 | Announcements | Authorized faculty/admin users shall create, edit, publish, and archive announcements. |
| FR-06 | Assignments | Authorized faculty users shall create assignments containing title, description, deadline, and course. |
| FR-07 | Service requests | Students shall create requests with category, description, and optional attachment metadata. |
| FR-08 | Request workflow | Authorized staff shall update request status such as Submitted, In Progress, and Resolved. |
| FR-09 | Notifications | The system shall provide in-app notifications for important announcements and request updates. |
| FR-10 | User management | Administrators shall create, update, deactivate, and assign roles to user accounts. |
| FR-11 | Search | Users shall be able to search relevant announcements, assignments, or requests within their permissions. |
| FR-12 | Audit information | The system shall record important administrative and workflow actions with timestamps. |

# 7. Non-Functional Requirements

| ID | Category | Requirement |
| --- | --- | --- |
| NFR-01 Performance | Common pages should load within an acceptable target under normal expected usage. |  |
| NFR-02 Availability | The MVP should target reliable availability during institutional operating hours. |  |
| NFR-03 Security | Passwords and sensitive information must be protected; access must be authorized by role. |  |
| NFR-04 Privacy | The system should collect only information necessary for defined functions and follow applicable institutional policies. |  |
| NFR-05 Usability | A first-time student should be able to locate timetable and announcements without extensive training. |  |
| NFR-06 Accessibility | The interface should follow practical accessibility principles such as keyboard navigation, readable labels, and adequate contrast. |  |
| NFR-07 Maintainability | The codebase should use modular components, meaningful naming, documentation, and version control. |  |
| NFR-08 Scalability | The architecture should allow additional users and modules without a complete redesign. |  |
| NFR-09 Compatibility | The application should support current major desktop and mobile browsers. |  |
| NFR-10 Backup & Recovery | Important data should be backed up according to an agreed operational policy and recovery procedure. |  |

# 8. Assumptions, Constraints & Dependencies

## 8.1 Assumptions

The institution will provide authorized test users and sample academic data.

Users have access to a modern web browser and internet connection.

Stakeholders will review requirements and prototypes within agreed review windows.

The MVP will initially support a limited set of roles and workflows.

## 8.2 Constraints

Internship project time and team capacity are limited.

The first release should prioritize essential features over advanced customization.

Production deployment may require institutional security, hosting, and policy approvals.

## 8.3 Dependencies

Authentication/identity provider or approved credential system.

Hosting environment and database service.

Institution-provided academic data and role definitions.

Email or notification service if external notifications are added later.

# 9. Project Scope

## 9.1 In Scope

Responsive web application.

Student, Faculty, and Administrator roles.

Secure login and role-based authorization.

Dashboard, announcements, timetable, assignments, service requests, notifications, and basic reports.

Basic audit history and administrative user management.

Database design, API/backend services, frontend screens, testing, documentation, and deployment preparation.

## 9.2 Out of Scope for MVP

Native Android/iOS applications.

Online fee payment and banking integrations.

Full learning-management functionality such as video classes and examination engines.

AI-based academic recommendations.

Biometric attendance hardware integration.

Complex analytics/data warehouse capabilities.

Multi-institution tenant management.

Scope control is important because adding features without adjusting time, budget, or resources can cause schedule delays and reduce product quality. New requirements should therefore be recorded, assessed, prioritized, and approved through a simple change-control process.

# 10. Requirements Prioritization

| Priority | Meaning | Examples |
| --- | --- | --- |
| Must Have | Essential for MVP acceptance | Login, roles, timetable, announcements, requests |
| Should Have | Important but can be adjusted if time is limited | Search, notifications, basic reports |
| Could Have | Useful enhancement | Advanced filters, richer dashboards |
| Won't Have Now | Explicitly deferred from MVP | Native mobile app, AI recommendations |

# 11. Development Timeline & Milestones

| Week | Phase | Key Activities | Milestone / Deliverable |
| --- | --- | --- | --- |
| 1 | Planning & Requirements | Stakeholder analysis, elicitation, user stories, scope, risks | Approved requirements document |
| 2 | System Design | Architecture, database model, API design, UI wireframes | Design specification |
| 3 | Environment & Foundation | Repository, project setup, authentication foundation, database | Working technical baseline |
| 4 | Core Development | Dashboard, timetable, announcements, assignment modules | Core feature build |
| 5 | Service Workflow | Requests, statuses, notifications, admin functions | MVP feature-complete build |
| 6 | Testing & Quality | Unit, integration, system, usability, security checks | Test report and defect fixes |
| 7 | Deployment & Documentation | Deployment preparation, user guide, technical documentation | Release candidate |
| 8 | Review & Handover | Stakeholder UAT, final corrections, demo, retrospective | MVP handover and final report |

# 12. High-Level System Flow

User → Login → Role Validation → Dashboard
                 ↓
   ┌─────────────┼──────────────┐
   ↓             ↓              ↓
Academic Info  Service Requests  Notifications
   ↓             ↓              ↓
Database ← Backend/API → Audit & Reporting

# 13. Risk Analysis & Mitigation

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| Unclear requirements | Medium | High | Use interviews, prototypes, acceptance criteria, and stakeholder sign-off. |
| Scope creep | High | High | Use MVP priorities and formal change-control review. |
| Security weaknesses | Medium | High | Apply role-based access, secure authentication, input validation, and security testing. |
| Schedule delays | Medium | High | Break work into milestones, track dependencies, and prioritize critical features. |
| Poor user adoption | Medium | Medium | Conduct usability testing and incorporate representative user feedback. |
| Data quality issues | Medium | Medium | Validate inputs and define data ownership and correction procedures. |
| Integration failure | Low/Medium | Medium | Prototype external integrations early and keep fallback options. |
| Insufficient testing | Medium | High | Create a test plan early and reserve dedicated time for defect fixing. |

# 14. Acceptance Criteria & Evaluation

All Must-Have requirements are implemented and traceable to approved user stories.

Each major user story has clear acceptance criteria and has passed testing.

Role-based access prevents unauthorized feature access.

Core workflows—login, timetable viewing, announcement publishing, and request tracking—work end to end.

The interface is usable on common desktop and mobile screen sizes.

Critical defects are resolved before final handover.

Required documentation includes setup instructions, user guidance, and known limitations.

Stakeholder/User Acceptance Testing confirms that the MVP meets agreed business needs.

# 15. Requirements Traceability Approach

A lightweight Requirements Traceability Matrix (RTM) will connect each requirement to a user story, design component, implementation task, and test case. This makes it easier to confirm that no important requirement has been forgotten and provides evidence during evaluation.

| Requirement | User Story | Design/Module | Test Evidence |
| --- | --- | --- | --- |
| FR-01 Authentication | US-01 | Authentication module | Login success/failure tests |
| FR-04 Timetable | US-02 | Timetable module | Schedule display tests |
| FR-07 Service request | US-04 | Request module | Create request test |
| FR-08 Workflow | US-05 | Request workflow | Status transition tests |
| FR-10 User management | US-08 | Admin module | Role/user management tests |

# 16. Development Methodology

The project can follow an Agile-inspired iterative approach. Work is divided into small increments, with requirements reviewed before implementation and feedback gathered after each usable feature set. A simple workflow can be: Backlog → Analysis → Development → Code Review → Testing → Stakeholder Review → Done. This approach reduces the risk of building a large system based on misunderstood requirements.

# 17. Deliverables

| Deliverable | Purpose |
| --- | --- |
| Requirements Document | Defines stakeholder needs, functional/non-functional requirements, assumptions, and scope. |
| User Stories & Use Cases | Explains how each user interacts with the system. |
| UI Wireframes | Shows proposed screens and supports early usability feedback. |
| Architecture & Database Design | Defines technical structure and data relationships. |
| Source Code & Version History | Provides the implemented software and development record. |
| Test Plan & Test Report | Demonstrates quality verification and defect management. |
| User & Technical Documentation | Supports usage, maintenance, and handover. |
| Final Demo / UAT Sign-off | Confirms that the MVP satisfies agreed acceptance criteria. |

# 18. Conclusion

This project plan demonstrates how a Junior Software Developer Intern can approach software development before writing substantial code. The most important lesson is that successful software begins with a clear understanding of the problem, the users, and the expected outcomes. CampusConnect has been deliberately defined with a controlled MVP scope, measurable requirements, user stories, use cases, functional and non-functional requirements, a realistic timeline, and a risk-management plan. The proposed process also creates traceability from stakeholder needs to implementation and testing. If approved, the next phase would be system design, including architecture, database schema, API contracts, security design, and responsive UI wireframes.

# 19. Reference Frameworks & Good-Practice Sources

ISO/IEC/IEEE 29148 — Requirements Engineering: guidance for requirements processes and requirements information.

Agile/Scrum principles — iterative delivery, backlog prioritization, stakeholder feedback, and incremental improvement.

INVEST principles for user stories — Independent, Negotiable, Valuable, Estimable, Small, and Testable.

MoSCoW prioritization — Must Have, Should Have, Could Have, Won't Have.